## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
RSI | Wrists could be aching | Ensure I move wrists about | To keep my wrists safe for the future | Moderate | Minor
Computer Failure | Software/hardware failure on my desktop could prevent me from using it | Installed development software (Node, VS Code, etc) on laptop | Have a back up computer to continue working on from latest github commit | Unlikely | Hazardous
Long-term internet outage | Issues could arise with internet provider or the wider system preventing internet access | Depending on cause, could use mobile phone as a hotspot, otherwise prioritise issues which can be moved forward without internet access. | Minimize or avoid down-time due to loss of internet connection | Very Unlikely | Major
Personal/family emergency | Illness, injury or other crisis could occur and need to be dealt with as a priority | Notify Stakeholders as soon as possible with potential time frame for impact | Ensure stakeholders are notified of unavoidable delays as soon as possible so they have the opportunity to adjust their plans | Very Unlikely | Hazardous
Trainer/QA emergency | Illness, injury or other crisis could occur and need to be dealt with as a priority | Ensure I already have at least the majority of the information/support needed to complete the project | To be able to continue working independently until the external crisis is resolved | Very Unlikely | Minor
Limited knowledge/experience | Potential for unforseen difficulties due to lack of experience with various technologies | Try and limit what we attempt so it is within/close to our current level of experience | To ensure the MVP is completed within the time frame | Likely | Major
Unauthorised access of data | Outside actors could attempt to access the sensitive data contained within our files, database and application | Ensure the data is always stored in a way that requires at least password authentication to access | To ensure the data is only viewed by authorised personnel | Moderate | Hazardous
Data Loss | Hardware failure or personal error could result in deletation of all data | Multiple backups of raw data and database | To ensure there is always some version of the data to go back to | Unlikely | Hazardous
Merge Conflicts | Multiple team members working in github simultaneously could result in merge conflicts, other git issues. | Following best practice: communicating often and checking and approving each others pull requests | To ensure as smooth as possible development experience and avoid complex git issues | Unlikely | Major
Scope Change | Customer/product owner could make large changes to requirements mid-project, or original brief could be misunderstood | Clarify queries with customer/product owner at beginning, but also be open to changes and adaptable | To ensure the project starts out on the right footing whilst being ready to alter development as necessary | Moderate | Minor
Time Constraints | Project has a very limited timescale leaving limited scope for learning, experimentation and errors | Focus on creating MVP, be willing to cut desired functionality for a working product, use known technology. | Provide working software at the end of the project even if it means sacrificing some aspects of the brief | Moderate | Moderate
Long-term power outage | Power failure on a local or wider scale | If local, notify stakeholders as soon as possible with potential time frame for impact, if wider, notify QA if possible. | Maintain communication where possible, focus on any opportunities to progress available | Very Unlikely | Hazardous
Global Pandemic | A virus could spread across the entire planet killing millions and infecting hundreds of millions | Get vaccinated | Just keep going, one way or another | Super Unlikely | Still working that out